Scott Harrell, Superintendent

2019-20

## Planning and Decision-Making Team

| Name Role. |
| --- |
| Sandra Trillo | Parent |
| Monty Edwards | Business |
| Shawnda Martin | Community |
| Tara Provence | Community |
| Tim Rodriguez | Community |
| Jenny Polk | Community |
| Vince Montes | Parent |
| Justin Bellar Misty Garza | Parent Parent |
| Warren Swarb | Teacher |
| Tonja Edens | Teacher |
| Joyce Welty | Teacher |
| Breanne Carter | Teacher |
| Debra Alanis | Teacher |
| Kayela Harrell Meagan Sowder | Counselor Counselor |
| Jonathan Robertson | Teacher |
| Leigh Thomason | Teacher |
| Trent Houchin | Teacher |
| Julee Patterson | Teacher |
| Kami Groetken | Teacher |
| Daniel Gutierrez | Teacher |
| Gordon Martin | Principal |
| DeAnn Wilson | Principal |
| Scott Harrell | Superintendent/Chair |

## Sudan ISD Vision Statement

Sudan ISD believes in:

Community

Integrity

Innovation

Tradition

We cultivate an environment where education is handmade, equipping students with the tools to be resilient, capable citizens.

Sudan ISD Main District Goals

Sudan ISD will manage resources to adequately fund school programs while maintaining financial soundness.

Sudan ISD will create an environment that attracts, retains, and supports passionate teachers that embody the district’s values and vision.

Sudan ISD will provide each student the opportunity of active engagement for a successful school experience that will foster the love of learning.

## Sudan ISD Direct Goals and Objectives

Goal 1:  All students, including the target populations, will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success

Objective 1:  All Sudan ISD students, including target populations, will demonstrate increases in student performance on STAAR/EOC Reading/ELA to meet or exceed state standard

Objective 2:  All Sudan students, including target populations, will demonstrate increases in academic performance on STAAR/EOC Math to meet or exceed state standards

Objective 3:  All Sudan students, including target populations, will demonstrate increases in academic performance

On STAAR/EOC writing to meet or exceed state standards

Objective 4:  All Sudan students, including target populations, will demonstrate increases in academic performance

On STAAR/EOC Science and Social Studies to meet or exceed state standards

Objective 5:  All Sudan students, including target populations, will take the ACT/SAT and will exceed 70%; and of those, 50% or more will meet or exceed state criterion scores

Objective 6:  All Students in Special Programs will meet or exceed state standards as indicated by the TAPR report.

Objective 7:  Students will take technology-related courses and use technology in classes that will enable them to be successful members of society

Goal 2:  Students will demonstrate behaviors that support academic success

Objective 1:  The retention rate will be reduced for all student groups

Objective 2:  Sudan will have a reduced number of disciplinary referrals from the previous year

Objective 3:  Sudan ISD will achieve and maintain a drop-out rate of 0% for all students and all student groups

Objective 4 Sudan ISD will achieve and maintain an attendance rate of 98% or higher

Objective 5:  Students will participate in programs to improve their self-esteem as evidenced by surveys and incident reports

Goal 3:  Sudan teachers will be provided technology and professional development to ensure student academic success

Objective 1:  Teachers will participate in intensive, sustained, research-based staff development in the areas of technology, TEKS, and STAAR/EOC

Goal 4:  Sudan ISD will develop a partnership with parents and all stakeholders to educate students to their highest level of academic success while fostering positive social, cultural, and emotional development.

Objective 1:  Sudan will involve all parents in their children’s education as measured by documented contacts

Sudan ISD

Target Populations

Economically Disadvantaged

African-American

Hispanic

White

Migrant

Male

Female

At-Risk

Homeless

Limited English Proficient

Special Programs

Career and Technology Education (CTE)

Dyslexia

English as a Second Language (ESL)

Gifted and Talented (GT)

High School Allotment

Special Education (SPED)

State Compensatory Education (SCE)

Title I, Part A:  Schoolwide (Title I)

Title II, Part A:  Teacher & Principal Training and   Recruiting (TPTR)

Title III:  Limited English Proficient (Shared Services Arrangement)

Title IV:  Student Support and Academic Enrichment

Goal 1:  All students, including the target populations, will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 1:  All Sudan ISD students, including target populations, will demonstrate increases in student performance on STAAR/EOC Reading/ELA to meet or exceed state standard.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Continue Reading Renaissance (RR) for daily practice reading | Reading Staff | Daily | TIA, TIV Local | RR computer Tests STAAR | STAR TPRI |
| Continue Schoolwide Title I program | Principal | Daily | TIA | 6 weeks grades | STAAR TPRI |
| Schedule 2 periods for reading for PK-3 for intense, individualized instruction as needed - iStation Pk-7 - 3 week summer program - Saxon phonics K-2 - Texas Treasures Phonics 1-2 - Study Island - RtI Benchmarking- Eduphoria Assessment & Diagnostic | PK-3 T Resource T RtI Teacher Teachers Reading Teachers | Daily and summer Daily Each 6 Weeks Each 6 Weeks | TIA, TIV Local Local Local | T Observation STAR Early Literacy Teacher Tests 6 Week Scores | TPRI Scholastic School Readiness Star Early Literacy ITBS State Assessments State Assessments |
| Engage Parents - Send STAR Reading Reports - Renaissance Reports - TPRI Reports - Study Island Reports | Teachers | Each 6 weeks | Local | Renaissance Reports | STAR |
| Notify parents of PK program for eligible students - by newspaper and posted bulletins - In English/Spanish | Principal | Spring | Local | Notification draft | Notification documents |
| Prioritize TEKS objectives during classroom instruction and provide Tutorials before/after school | Math Teachers | January through April Testing Date. | High School Local $4,000 | Teacher made and Released STAAR tests for Pre and Post-tests. | Released STAAR/ EOC Exam View Computer Software Teacher Made Tests. Graphing calculators Local; Measuring Up; Moodle; |
| Teachers and Students will be provided test-taking strategy training. | Core subject teachers | Two weeks prior to STAAR test | Local Curriculum Contract Titile I, Title II, TPTR | Teacher observation Pre test STAAR | STAAR/ EOC |
| Provide Review Classes for students not mastering STAAR/EOC objectives | Math teachers | August until STAAR | Local | Teacher observations | STAAR/ EOC |
| Implement vocabulary & literary element workbooks & applications | ELA teachers | Released STAAR tests Teacher observations. | Local High School Allotment | Local | STAAR/ EOC |
| Prioritize TEKS objectives during classroom instruction | Teachers | Teacher made and Released STAAR tests for Pre-and Post- tests. | January through March Testing Date. | Local | Released STAAR tests. |
| Train Teachers to provide test-taking strategies | Teachers | Teacher observation Pre-test STAAR | Two weeks prior to STAAR test | Title I & II TPTR | STAAR/ EOC |
| Provide reviews with release STAAR/EOC tests and study guides | ELA teachers | Teacher tests | August – April | Local | STAAR/ EOC |
| Study Island & iStudent, Accelerated Instruction Plans | Teachers | Teacher tests | Quarterly | Local | State assessments |
| Peer Editing | Teachers | Teacher tests | Quarterly | Local | State assessments |

Goal 1:  All students, including the target populations, will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 2:  All Sudan students, including target populations, will demonstrate increases in academic performance on STAAR/EOC Math to meet or exceed state standards.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Target problem solving strategies and applications - Use games & manipulatives - Peer tutoring - Accelerated instruction - Use Study Island program, Math Facts in a Flash - Target measurements/ estimation - STAAR Target practice in 2-7 classrooms daily - Hold vertical alignment meetings K-7 - Schedule additional period for K-7 | Math teachers Math Team Leader | Daily Monthly | Local TIA $4,000 High School Local Local | TOPS reports AMI reports Progress Reports | TPRI STAAR STAR ITBS Scholastic School Readiness |
| Provide RtI for additional period | Principal | August | Local | Progress Reports | STAAR |
| Review classes for students not mastering STAAR objectives | ELA teachers | August | Local | Released STAAR tests Teacher observations. | STAAR/ EOC |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 2:  All Sudan students, including target populations, will demonstrate increases in academic performance on STAAR/Math to meet or exceed state standards

| Strategies | Resources | Formative Evaluation | Timelines | Staff Responsible | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Prioritize TEKS objectives during classroom instruction | Local | Teacher made and Released STAAR tests for Pre-and Post- tests. | January through March Testing Date. | Math teachers | Released STAAR tests. |
| Train Teachers to provide test-taking strategies | Title I & II TPTR $500 | Teacher observation Pre-test STAAR | Two weeks prior to STAAR test | Administrator | STAAR/ EOC |
| Provide reviews with release STAAR tests and study guides | Local High School Local $500 | Teacher tests | August – April | Math teachers | STAAR/ EOC |
| Go Math Curriculum, Lonestar Target, Education Galaxy, & Imagine Math 3-8 | Local TIA, TIV | Teacher tests | Quarterly | Teachers | State assessments |
| Peer Editing | Local | Teacher tests | Quarterly | Teachers | State assessments |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 3:  All Sudan students including target populations will demonstrate increases in academic performance on STAAR/EOC writing to meet or exceed state standards.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Align grades K-7 to implement consistent strategies and target writing objectives - Provide local teacher training - Presented by teachers - Use Study Island Program for writing - Individualized to student needs - Benchmarking - Departmental and Cross Curricular Meetings and Workshops | Writing teachers | June-September | Local TII | Training planned and scheduled | Training sign in sheets STAAR writing |
| Encourage participation in UIL, Reading Readiness, Spelling and Grammar | Teachers | Fall | Local | List of students involved | Students participating |
| Prioritize STAAR/EOC writing objectives during classroom instruction | ELA teachers Core subject teachers | August-May | Local TITLE I High School Local $250 | Teacher made and Released STAAR tests for Pre and Post tests. | Released STAAR tests. |

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Curriculum & Programs Use Empowering Writers Program for writing 2-4 & iStation Pk-7 | Writing Teachers Administrator | Aug-May | Local | Teacher Observation Writing Benchmarks iStation Reports | Training sign in sheets STAAR writing |
| Emphasize the development of writing skills in all classes using STAAR/EOC study guides | Entire faculty | August - May | Local TIA & TII $300 | Use of writing exercises in all classes. STAAR writing material | STAAR/ EOC Writing exams |
| Provide reviews with released tests and auxiliary reading materials | ELA teachers | August – March | Local High School Local $500 | Open ended questions and teacher made tests | STAAR/ EOC |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 4:  All Sudan students including target populations will demonstrate increases in academic performance on Science and Social Studies STAAR/EOC to meet or exceed state standards.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Add additional time per week for science TEKS in 5th | Administrator | Weekly | Local | 6 Weeks grades Benchmarking | STAAR |
| Align curriculum at K-7 grades for STAAR /TEKS objectives | Science teachers | Monthly | Local | Curriculum meetings | STAAR TSDS |
| Curriculum & Programs STEMScopes K-8 Science Scholastic News Education Galaxy | Science Teachers | Monthly | Local TIA TIV | Lesson Plans STEMScopes Reports Education Galaxy Reports | STAAR/EOC |
| Provide students and Teachers with training in test-taking strategies | Subject area teachers | Daily | TIA $100 TII TPTR TIV SSAEP | 3 week placement identification Study Island | Study Island |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 5:  All Sudan students, including target populations, will take the ACT/SAT and will exceed 70%; and of those, 50% or more will meet or exceed state criterion score.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Utilize computer software during class time 11-12 grades | Administrator ELA teachers | August – Dec test date | TIA & TII High School $500 | Computer software assessment ACT/SAT prep software | ACT/SAT scores |
| Will provide ACT testing center at High School | Dyslexia staff | August | Local | Number of participants | Written procedures |
| Target all ACT/SAT test date for student participation & administer pre ACT & SAT assessments | Counselor Administrator Teachers | August-June | Local | Pre-ACT 10th grade ACT 11th-12th grade | ACT/SAT scores |
| Provide students with intense preparation prior exams | Mr. Robertson Counselor | November | Local TIA & TII $2,000 High School Local $2,000 | Observation of students | Improvements in overall ACT scores. |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

# Career and Technology Education (CTE)

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Provide CTE courses | School Board | Early Aug. and upon enrollment | CTE $9,000 High School $5,500 | List of courses offered | # of students with 4-year plans on file |
| Conduct Comprehensive Needs Assessment - STAAR - STAAR/ Participation - LEP Dropout - AMAOs - STAAR/EOC/Cross Curriculum/Kinetic Learning | CTE staff Administrator | Local | CTE Staff | Upon release of TAPR | PBMAS |
| Provide CTE Professional Development - Teachers and paraprofessionals - Research-based - Based on staff needs | Administrator | During year and summer | Local Title IV SSAEP CTE $100 | Training scheduled | Certificates of training |
| Conduct comprehensive needs assessment (CNA) to determine CTE program strengths/needs | Principal CTE staff | May-July | Local CTE $3,000 TIV SSAEP High School $5,500 | Upon release of TAPR | Annual CTE evaluation |
| Provide vocational & technical education programs to all eligible students and help students receive license/certifications | School Board administration; Local; Title IV SSAEP | August | Local TIV SSAEP | Students choice cards | Fully certified staff; Students earning licenses/certifications/CTE Credits |
| Conduct comprehensive needs assessment & program evaluation to determine effectiveness of CTE programs | CTE staff | May | CTE funds Surveys | Data disaggregated | Training certificates |
| Local advisory council reviews and updates objectives to ensure relevance to business/industry | CTE staff | Fall Spring | CTE funds | Mid-year review | Communications for year |
| Integrate CTE & academic programs | CTE staff | On-going | TECH prep | Meeting records Written plan to integrate | CTE Evaluation |
| Encourage students to pursue coherent sequence of courses with a 4 year plan | Counselor | Spring | Local | Choice cards | Program evaluation |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

Dyslexia

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Identify students with dyslexia/related disorder & provide services | Administrator | August/ January | Local SCE $1,000 | Staff training record | List of identified students |
| Provide Herman Method program | Administrator | August | Local | Program materials Written procedures | STAAR |
| Align SBOE procedures and district/campus procedures annually | Administrator | August | Local | Draft of written procedures | Adopted written procedures |
| Provide services for students who may be eligible under 504 | 504 Committee | Daily | Local | List of identified students | List of students served |
| Provide research-based staff development for staff | Superintendent | Summer | Local | Training scheduled | Teachers training certificates |
| Ensure teachers have proper qualifications | Superintendent | Spring Summer | Local | List of teachers providing services | Teaching certificates |
| Provide parent involvement opportunities | Counselor | Quarterly | Local | SPIN meetings | Attendance sign in |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

English as a Second Language (ESL)

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Identify and provide all LEP students an ESL program to develop proficiency in comprehension, speaking, reading, and composition of English | ESL teachers | August and upon student enrollment | ESL Local TIII (SSA) | Home Language Survey List of students | TELPAS STAAR/EOC |
| Conduct Comprehensive Needs Assessment for students: STAAR, AMAOS | ESL staff Principals | Fall | Local | Meeting Agenda and minutes | STAAR/EOC |
| ESL students will participate in programs designed to enable them to reach or exceed state standards- English in a Flash | ESL staff | Quarterly | Local ESL TIII (SSA) SCE $1,000 | 6 week grades | STAAR/EOC TELPAS |
| Provide research-based staff development for teachers and paraprofessionals | Principals | August – May | ESL Local TIII | Training scheduled | Sign-in sheets for training |
| Send communications to parents in home language of parents as appropriate | Principals | Year-round | Local | Communications | Communication to parents |
| Identify & provide LEP students a program that develops proficiency in comprehension, speaking, reading, & composition of English | ESL teachers | Upon student enrollment | Local ESL funds | Home Language Survey List of ESL students | STAAR/EOC TELPAS |
| Provide parent involvement opportunities | Counselor | Quarterly | Local | SPIN meetings scheduled | Attendance sign in sheets |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

Gifted and Talented (GT)

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Offer advanced placement classes in High school | GT Coordinator | August – May 2007 | Local Teacher training | Number of classes offered | Number GT enrolled in AP classes |
| Modify in grades K – 12 for GT students | Counselor | August – May | Local GT $2,100 | Lesson plans | T-TESS STAAR/EOC |
| Participate in Level I ESC Cooperative | Superintendent | August – May | GT funds Local | ESC G/T activities | STAAR/EOC |
| Continue to update policy | Administrator | August | Local | Agenda | Policy update |
| Provide parent involvement opportunities | Counselor | Quarterly | Local | SPIN meetings scheduled | Attendance sign in sheets |
| Provide 6 hours annual update for professional staff | Supt. | Fall | Local GT $2,100 | Training scheduled | Hours |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

State Compensatory Education (SCE) SCE funds will be coordinated with Title I funds at the two Schoolwide campuses with 40% or more low-income percentage to serve at-risk students.  Summary totals:  $          FTEs

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Coordinate SCE and Title I funds on the Schoolwide Campus with 40% or more low income to serve at-risk students | Administrator | August - July | SCE 1 FTE’s $57,852 TIIA $5,000 SCE $12,350 | Progress Reports Teacher Observations | STAAR/EOC |
| Determine campus and district SCE budgets and document in plans | Superintendent Principals | August | SCE $500 and FTEs for Schoolwide campus programs | Budgets | DIP CIPs |
| Continue to encourage enrollment in career-technology programs | At-Risk coordinator | August – May | CTE Local | Number of students enrolled | Students enrolled |
| Provide PEP alternative campus (academic) for students with special needs | Counselor | August –May | $500 SCE Local | Students enrolled at PEP | Students enrolled at PEP and graduation rate/GED |
| Small class sizes for acceleration | Teachers | August – May | $1,000 SCE Local | 6 week grades | End of year grades/STAAR/EOC |
| Provide tutorials | Principals | August – May | SCE/Local | Students enrolled | STAAR/EOC |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

# SCE, Continued

| Strategies | Resources | Formative Evaluation | Timelines | Staff Responsible | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Evaluate At-Risk program by comparing at-risk group to all student group in reading, math, writing, and Completion Rates | Local SCE $500 | Report card grades | May | Superintendent Principals | STAAR/EOC/ reading/math and completion rate chart of at-risk and all other student |
| Provide research-based staff development for teachers concerning at-risk strategies | Local SCE $500 | Training schedule | August – May | Counselor | Sign-in sheet for training sessions |
| Provide counseling/instruction in pregnancy prevention/abstinence | Local Lamb County Extension service | Principal observations | August – May | Counselor | PRS report |
| Encourage pregnant students to remain in school and also provide homebound instruction as needed | Local SCE $500 | Number of students remaining/ receiving instruction | As needed | Counselor | Percent of pregnant/parenting students graduating |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success

.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

Special Education (SPED)

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Ensure students with disabilities have access to general curriculum | SPED teachers | August – May | SPED 5 FTE’s $168,137 Local | ARD/IEP | Student schedules |
| Provide individualized instruction on STAAR/EOC subject areas | SPED teachers | August – May | Released tests SPED $750 | Release Tests | STAAR/EOC |
| Establish timeline for evaluation: Systematic process for pre-referral is established | SPED teachers | August – May | Referral packet SPED | Grades | ARD records |
| Establish least restrictive environment and placement decision to include annual determination of LRE | SPED teachers | August – May | SPED |  | ARD records |
| Consider related services based on student needs | Principals SPED Co-op | August – May | SPED Co-op | Testing results/observations | ARD meeting minutes |
| Provide research-based staff development with staff input including: - How to modify curriculum - Pre-Referral Process | Administrator | Training calendar | SPED $100 Local | As scheduled | Training certificates |
| Provide Parent Involvement opportunities for parents to participate in school activities | SPED Dr. | Monthly | Local SPED $100 | SPED Dr. | Sign in sheets |
| Put operating guidelines and tracking system in place as Timeline for Reevaluation | SPED Director | August – May | SPED policy land procedural manual | Eligibility folders | Review of re-evaluation ARDs |
| SPED students will show improvement on STAAR/EOC, or other alternative assessment | SPED teachers | August – May | SPED Local | Grades | STAAR/EOC TPRI |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 6:  All Students in Special Programs will meet or exceed state standards on the STAAR/EOC or alternative assessments.

Title I, Part A:  Schoolwide Title I Program

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Conduct Comprehensive Needs Assessment to determine needs and plan instruction - STAAR/EOC for Special populations - Annual Measurable Achievement Objectives (AMAOs) for Limited English Proficient students - PBMAS Report - Economically Disadvantaged | Administrators | Fall | Local TIA $100 | Meeting agenda | STAAR/EOC AMAO |
| Plan reform strategies to address needs - Focus: Economically disadvantaged - Focus: At-Risk - Include extended day / year - Provide aides for tutoring/acceleration | Site-Base Team, Chair | Quarterly | Title I $100, TIIA, TIV ESL, SCE-$100 TIII $100 | Caps and strategies | STAAR/EOC |
| Provide instruction by qualified aides and teachers who are certified in their field: - Limit interviews for new teachers to certified applicants - Assist teachers with exam preparations and use federal Title funds to pay for exams - Provide incentive pay and benefits above state average to attract and retain teachers - Paraprofessionals hired after 1/8/02 will be qualified when hired | Superintendent | Quarterly | Title I $100, TIIA $100 TPTR, Technology, Local | CIPs and strategies | STAAR/EOC |
| Provide staff development for teachers, paraprofessionals - Based on input from staff intensive, sustained, research-based | Principals | Staff Development Days | Title I $100, local, TIIA $100, Title II, TIV | Staff Development Calendar | STAAR/EOC |
| Attract certified staff to high needs areas and campuses | Administrators | Summer | Local Title I $100, TII TPTR | Personnel Files | Personnel Files |
| Increase parent involvement with SPIN Meetings /activities planned - Designed to improve student academic achievement - Designed for parents to have opportunities to participate in decisions regarding their child’s education | PI Coordinator | Monthly | Title I, Local | PI Events | PI Evaluation |
| Assist pre-school/Head Start children to next grade with visitation time for kids & parents | Elem. Principal | May | Title I | Event planned On calendar | Sign-In sheet |
| Provide parent communications: Conference with parents Hold flexible number of meetings | Principal | Aug-July | TIA $100 | Communications to parents each 6 weeks | Parent & Family engagement evaluation |
| Identify students who need extra assistance to meet state standards | Lead teachers | Each reporting period | Title I | List of identified students | STAAR/EOC |
| Conduct Annual Title I Meeting/Back to School Night -Inform parents of TIA program -Explain parents’ rights to be involved -Revise Parent Compact in English/parents home language Coordinate and integrate federal/state, local programs | Principals | Fall | Local Title I$100, Title II$100 Title IV ESL SPED, GT CTE$100, SCE$100 | Meeting agendas Sign In Sheet | Agenda and Sign in sheet |
| Evaluate Parent Engagement program - Involve parents | Principal | Spring | Title I $100 | SB Meeting Agenda | Evaluation results |
| Review Parent Engagement policy - Developed & agreed upon by parents each year - Copies distributed | Administrator | Summer | Local | Meeting agenda | Policy |

Goal 1:  All students, including the target populations will reach or exceed state academic performance standards for a “Met Standard” rating on State accountability in order to achieve lifelong success.

Objective 7:  All Students will take technology-related courses and use technology in classes that will enable them to be successful members of society.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Provide opportunities for using computers in classroom work | Principals | Year-round | Local Tech Lab | Lesson Plans | Lesson Plans |
| Require 8th graders to take word processing | Counselor, Administrator | August | Local Technology | Student schedules | Student schedules |
| Require all students to take one technology applications course before graduation | Counselor, Administrator | Year-round | Local | Four year plans | Transcripts |

Goal 2:  Students will demonstrate behaviors that support academic success.

Objective 1:  The retention rate will be reduced for all student groups.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Ask Parents/community volunteers to tutor one-on-one for specific needs of students | Principals |  | Local | List of volunteers | Promotion rate |
| Set up daily tutoring as needed | Principals |  | Local Title I SCE | Attendance at tutorials | Promotion rate |
| Provide optional summer program for acceleration and enrichment | Principal |  | Local SCE | Attendance | Promotion rate/ AR points accumulated |

Objective 2:  Sudan will have a reduced number of disciplinary referrals to principals from the previous year.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Rewards will be provided for students for good behavior (field trips in the Spring) & Positive Behavioral Intervention System (PBIS) | Principal | May | Local | Referrals | Referrals |
| Involve parents as partners in education | Principals | Year-round | Local | Discipline referrals | Discipline records |

Goal 2:  Students will demonstrate behaviors that support academic success.

Objective 3:  Sudan ISD will achieve and maintain a dropout rate of 0% for all students and all student groups.

| Strategies | Staff Responsible | Timeline | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Offer vocational and tech-prep courses | Principal | August – May | Local CTE SCE | Number of students enrolled | TAPR dropout rate |
| Promote self-esteem | Counselor | August – May | Guidance Lessons Local | Grades | Dropout rate |

Objective 4 Sudan ISD will achieve and maintain an attendance rate of 98% or higher for the 2019-20 school year.

| Strategies | Staff Responsible | Timeline | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Send letters to parents of excessive absences | Principals | Year-round | Local | Letters sent home | End of year attendance report |
| Recognize outstanding attendance by presenting awards and incentives– | Principals | August – May | Local | Six weeks attendance | Awards and incentives given |

Goal 2:  Students will demonstrate behaviors that support academic success.

Objective 5:  Students will participate in programs to improve their self-esteem as evidenced by surveys and incident reports.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Provide for awareness, prevention and education in these areas: - Unwanted physical or verbal aggression - Child Abuse and Neglect - Sexual harassment including sexting - Other forms of bullying - In schools, - On school grounds - In school vehicles - Dating violence | Principal Counselor | Year-round | Local TIV | Training calendar Handouts | PEIMS 425 incident records Surveys |
| Adopt policy & procedures for areas above to address: - Counseling needs - Awareness education - Training | Superintendent | Fall | Local | Policy & procedures | Training certificates Counseling Log Policy |
| Suicide prevention/conflict resolution training will be provided for all students. | Counselor | Year-round | Local Title lV | Referrals | Discipline reports |
| Participate in Peer Mediation training | Counselor | August – May | ESC 17 | Student participation | Surveys |
| Improve student fitness and health - Implement SHAC/TEA Coordinated School Health Instructional Program - Focus: K-7 - Participate in Fitness gram data entry for all grades - Provide parents with data | Principal, Nurse | Each 6 weeks | PE Curriculum PE teachers | Curriculum guides Fitness gram data entry | Fitness gram scores With increase from previous year |

Goal 3:  Sudan teachers will be provided technology and professional development to ensure student academic success.

Objective 1:  Teachers will participate in intensive, sustained, research-based staff development in the areas of technology, TEKS, and STAAR/EOC.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Provide staff development training in various technology programs | Technology directors | June – May | Local Title I Title II, Title IV | Training scheduled | Teacher sign-in sheets |
| Provide TEKS & Eduphoria staff development (implementation & curriculum alignment) | Principal | Year – round | Local Title II, Part A: TPTR contract Title I | Training scheduled | Teacher training certificates |
| Provide training in coordination of program | Superintendent | August – July | Local | Training scheduled | Training sign-in sheets |
| Provide training in core subjects | ESC 17 | August – July | Title II Curriculum Contract | Training scheduled | Attendance certificates |

Goal 3:  Sudan teachers will be provided technology and professional development training to ensure student academic success.

Objective 1:  Teachers will participate in intensive, sustained, research-based staff development.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Provide training in - Safe, drug free curriculum - Suicide prevention - Conflict resolution - Violence prevention - Integration of technology in instruction & administration - Discipline management | Administration, Counselor | August – June | Local | Training scheduled | Sign-in Sheets |
| Determine staff development needs based on state assessment data: (STAAR/EOC, TELPAS, TPRI) | Principals | August | Local | Staff meeting to look at campus and district student needs | Survey Results and staff development plan |

Goal 4:  Sudan ISD will develop a partnership with parents and all stakeholders to educate students to their highest level of academic success while fostering positive social, cultural, and emotional development.

Objective 1:  Sudan will involve all parents in their children’s education as measured by documented contacts.

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Hold regular meetings for Planning and Decision Making Team (Parents/business/community/staff collaboration) | Chair | Quarterly | Local | Meetings scheduled | Sign in sheets |
| Provide opportunities for parents to participate in school activities in special programs and general curriculum activities - Regular SPIN Meetings - Meet the Teacher Night - Back to School Night - Parent Conferences - Doughnuts with Dads/Muffins with Moms/Granola with Grandparents - Field Trips - Classroom activities - Holiday programs - End of year programs | Principals Teachers | Monthly | Local TIA | Parent Activities Calendar | Sign-in sheets |
| Inform parents of - State assessments - Proficiency levels required - General Curriculum - Higher education admissions - Financial aid opportunities Curriculum choices for success beyond HS | Principals, Counselor | August – May | Local Title I | Schedule of events | Sign-in Sheets Parent surveys |
| Hold Parent-Teacher conferences | Counselor Principals | September – May | Local | Conferences scheduled | STAAR/EOC Parent Sign-in Sheets |

| Strategies | Staff Responsible | Timelines | Resources | Formative Evaluation | Summative Evaluation |
| --- | --- | --- | --- | --- | --- |
| Continue PK Program for 4 year old students | Superintendent | August – May | Local Title I | Program activities | STAR and readiness tests |
| Inform parents of state assessments, proficiency levels, and local assessments in home language | Superintendent | Spring | Local | Meeting scheduled | Sign-in Sheet Minutes of meetings |
| Provide parents with information on the following: - Higher education admissions - Financial aid opportunities - Curriculum choices for success beyond high school | Counselor | September Spring | Local | Meetings scheduled | Parent Surveys |
| Survey parents to evaluate: - School climate - Special programs - Parent Engagement | Principals | Throughout year | Local Title I | Surveys developed and scheduled during year | Survey Results STAAR/EOC |

Comprehensive Needs Assessment

| #### Area of Review | #### Needs | #### Strengths | #### Priorities & How Federal/ State Local Funds will be used |
| --- | --- | --- | --- |
| Demographics | Annual assessment of low socioeconomic students/parents & provide services/programs | Reading, writing, and social studies scores continue to excel in all subgroups. Continue to address the needs of parents with SPIN meetings and parent/teacher conferences. | Continued emphasis on technology for At-Risk and all sub groups. Federal funds for one-on-one and small group reinforcement of skills and objectives. Technology is used to help at-risk students. |
| Special Program: Title 1 Schoolwide | Continue to annually assess the needs of at risk students; Provide qualified instructional aides on Elementary campus to work with at-risk students needing acceleration | Enhanced technology through Title programs. Parent involvement including SPIN meetings and parent/teacher conferences. | Technology and enrichment resources Continue using our parent involvement policies and practices. TIA & TIIA, TIV 3 FTE’s |
| Special Program: CTE | Update current curriculum for new courses to meet endorsements part of graduation plan. | Solid teaching staff in these programs. Continue to offer a variety of traditional and non-traditional CTE courses to both genders. Construct Master Schedule to give the students choices in their CTE courses. Continue to let the student choose their CTE courses in High School. | Purchase curriculum for new courses to meet endorsements part of graduation plan using State and Federal funds. |
| Special Program: English Language Learners LEP & Title III | Continue improvement in our ELL program. To continue to increase parental involvement. | Knowing and understanding the current ESL population and ways in which to instruct them effectively. Conducting 3 parent nights for partnering with ELL parents. | Continue to train staff on relevancy of TELPAS writing samples and professional development. Local & TIA |
| Special Program: State Compensatory Education for At-Risk | Continue to assess the needs of at risk students, especially in regard to math and science. Small class sizes when we can. Assistance for parents. | Enhanced technology resources for at risk students along with effectively addressing the needs of at-risk students and their parents through instruction, assessment, and parental involvement conferences. | Technology and enrichment resources. Federal and State funds. Continue using our parent involvement policies and practices. Federal Funds where applicable |
| Special Program: Special Education | - Continue to follow IEP’s. Purchase Inclusion curriculum where needed. | Closely following IEP and modification sheets. - Teachers and staff are aware of instructional strategies that enhance the learning of all students including those with special needs. | - Lamb County SPED Coop funds. - Local |
| Academic Achievement | To provide aides for tutoring and small group acceleration; To maintain high scores in all STAAR subjects. To increase all students’ math and science scores - To improve results for At-Risk students including English Language Learners, students with disabilities and students in poverty. - Produce more college ready students. Continue student ACT prep work. | - Currently performing well on State Tests. High graduation percentage. | - Continued emphasis on technology and assessment programs - Local and Federal funds. - More inclusion assistance for high rigor of college readiness. |
| Curriculum | To continue to align the TEKS with curriculum taught in classrooms. - Vertically align curriculum between grade levels. - Curriculum for new courses to meet endorsements part of graduation plan. | - Ability of teachers to use State/supplemental curriculum in educating students. Currently meeting high standards. - Benchmarks and assessments are closely monitored to ensure alignment between TEKS and curriculum is occurring. | - Purchase additional curriculum as needed for new CTE courses for endorsements part of graduation plan using state funds. |
| Instruction & Assessment | To maintain quality instructional strategies and assessments for the academic improvement of all students. To continue to align the TEKS with curriculum taught in classrooms. - Vertically align curriculum between grade levels. - More professional development in Region Materials Assessment tools with needs in ELA. | - Benchmarking methods. Bell to bell concept teaching. Teachers use a variety of instructional strategies and assessments on a daily basis. Professional development is provided to assist in areas of instruction and assessment as need. Benchmarks and assessments are closely monitored to ensure alignment between TEKS and curriculum is occurring. | - Local funds. - State funds |
| Staff Certifications, Recruitment, Retention | - Recruit/Retain quality teachers | - Veteran staff with many being here over 20 years. | - Local funds. |
| Professional Development | - More Eduphoria and technology training. - Training in Region Materials. | - Teachers are encouraged to attend professional development in their core subject areas as well as any other area of necessity. | - More Eduphoria PD through our ESC using Local funds. |
| Family and Community Engagement | - Continue to partner with parents in raising and educating our children. To build capacity and outreach to all parents of students. - To assist parents in ways to help their students at home. | - Participation in programs like “Youth in Service” and offering safety programs like “RAB.” (Remember Alex Brown) SPIN meetings are fairly well attended. The school includes all parents in school activities and functions. Information is provided to parents in their native language. - Parents are given information on state assessments and proficiency levels. - Develop policy with parents and family involvement, identify barriers to the engagement policy | - Give student the opportunity to participate in these programs using Federal funds. |
| School Culture, Climate & Organization | - School Vision - Trauma Informed Care Certifications | - Family friendly oriented environment. Positive culture and climate is attained through focusing on positive and affirmative behavior. Random acts of kindness are rewarded. - Development of Risk Assessment Teams | - Local funds as needed |
| Technology | To continue to provide technological assistance to staff. To continue to provide technological instruction to students and staff. - More laptops in the hands of HS students | - Great wireless internet system; Great infrastructure and connectivity; Excellent support staff. | - Possible laptops for more students using Federal, State, and Local funds. - Federal, state, and local funds as needed for additional technology and/or programs. |
| Summary of Data Reviewed: STAAR data; PBMAS data; Teacher observations; TAPR data; ACT score data. |  |  |  |